## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Image Processing | MUST HAVE | Opencv, Numpy, Pandas, Glob, Matplotlib | Prashant Singh | 3- Completed
S2 | S2 | US-002 | Object Detection | MUST HAVE | Ultralytics, yolov3-tinyu.pt model, Os | Prashant Singh | 3- Completed
S3 | S3 | US-003 | Object Tracking | MUST HAVE | Opencv, Ultralytics, yolov8n.pt model | Prashant Singh | 3- Completed
S4 | S4 | US-004 | Dense Optical Flow | MUST HAVE | OpenCV, Numpy | Prashant Singh | 3- Completed
S5 | S5 | US-005 | Sparse Optical Flow | MUST HAVE | OpenCV, Numpy | Prashant Singh | 3- Completed
S6 | S6 | US-006 | UI implementation for Image Processing | MUST HAVE | Flask, Os, Werkzeug, Numpy, Opencv | Prashant Singh | 3- Completed
S7 | S7 | US-007 | UI implementation for Object Detection and Object Tracking, and UI Integration | MUST HAVE | Flask, Os, Werkzeug, Opencv, yolov3-tinyu.pt and yolov8n.pt model, Ultralytics, Shutil, Subprocess | Prashant Singh | 3- Completed
S8 | S8 | US-008 | UI implementation for Dense Otptical Flow and Sparse Optical Flow, and UI Integration | MUST HAVE | Flask, Os, Werkzeug, Numpy, Opencv | Prashant Singh | 3- Completed
Note on F1: Mention the US ID(s) on which the user story depends. -Sumeet Kumar Barua08

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 12 | 8 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | TID-01 | Image Processing | 2024-11-04 | 2024-11-06 | Shiven Patel | Coding | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | TID-02 | Object Detection | 2024-11-07 | 2024-11-08 | Shiven Patel | Coding | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | TID-03 | Object Tracking | 2024-11-11 | 2024-11-11 | Shiven Patel | Coding | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | TID-04 | Dense Optical Flow | 2024-11-12 | 2024-11-15 | Shiven Patel | Coding | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | TID-05 | Sparse Optical Flow | 2024-11-16 | 2024-11-22 | Shiven Patel | Coding | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | TID-06 | UI implementation for Image Processing | 2024-11-23 | 2024-11-29 | Shiven Patel | Build | 3- Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | TID-07 | UI implementation for Object Detection and Object Tracking, and UI Integration | 2024-12-02 | 2024-12-06 | Shiven Patel | Build | 3- Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | TID-08 | UI implementation for Dense Otptical Flow and Sparse Optical Flow, and UI Integration | 2024-12-09 | 2024-12-13 | Shiven Patel | Build | 3- Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: 9/15/2016 or 15-Sep-2016 -Please enter the dates in either of these formats
Note on E2: 9/15/2016 or 15-Sep-2016 -Please enter the dates in either of these formats
Note on I3: This is the total task estimated in hours for all the user stories -Sumeet Kumar Barua08
Note on J3: Pending effort hours after completion of day 1 work -Sumeet Kumar Barua08
Note on K3: Pending effort hours after completion of day 2 work -Sumeet Kumar Barua08
Note on L3: Pending effort hours after completion of day 3 work -Sumeet Kumar Barua08
Note on M3: Pending effort hours after completion of day 4 work -Sumeet Kumar Barua08
Note on N3: Pending effort hours after completion of day 5 work -Sumeet Kumar Barua08
Note on O3: Pending effort hours after completion of day 6 work -Sumeet Kumar Barua08
Note on P3: Pending effort hours after completion of day 7 work -Sumeet Kumar Barua08
Note on Q3: Pending effort hours after completion of day 8 work -Sumeet Kumar Barua08
Note on R3: Pending effort hours after completion of day 9 work -Sumeet Kumar Barua08
Note on S3: Pending effort hours after completion of day 10 work -Sumeet Kumar Barua08
Note on T3: Pending effort hours after completion of day 11 work -Sumeet Kumar Barua08
Note on U3: Pending effort hours after completion of day 12 work -Sumeet Kumar Barua08
Note on V3: Pending effort hours after completion of day 13 work -Sumeet Kumar Barua08
Note on W3: Pending effort hours after completion of day 14 work -Sumeet Kumar Barua08

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Asked for notes on AI and tools | Conducted a detailed discussion with mentors and team
Sprint 1 | Day 4 | Query on OpenCV and TensorFlow topic | Conducted a team session and reviewed the project requirements with explanation
Sprint 2 | Day 6 | Agile template confusion | Conducted a meeting where all doubts were clarified by the mentor
Sprint 2 | Day 7 | Confusion on Object Detection | Conducted additional research and consulted about the code
Sprint 2 | Day 9 | Query on Object Tracking | Created a code to explain the use of modules on the tracking code
Sprint 3 | Day 12 | Query on Implementation of UI | Mentor explained how to create UI and granted permission to use any resource
Sprint 4 | Day 16 | UI model is created | Conducted a team session and reviewed the project UI implementation with explanation
Sprint 5 | Day 23 | Query on some mistakes or changes | Provided a solution to the issue and explained the process to solve it

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2024-11-04 | 2024-11-06 | Shiven Patel | Reviewing documentation regularly | Assuming project requirements are clear | Participating in discussions and meetings | Scheduled a review session with team and mentors to clarify project goals
2 | Sprint 3 | 2024-11-16 | 2024-11-22 | Shiven Patel | Prioritizing Python practice | Delaying review of tasks | Maintaining focus on coding | Achieved Python coding completion on time
3 | Sprint 4 | 2024-11-23 | 2024-11-29 | Shiven Patel | Preparing for project implementation | Rushing through understanding concepts | Asking for help when stuck | Completed all the tasks with support from the team
4 | sprint 5 | 2024-12-02 | 2024-12-06 | Shiven Patel | Participating in project discussions | Delaying UI Implementation | Collaborating for UI building | Completed UI Implementation properly and received team feedback for improvements